## Sheet1
Author - Eric Hanks |  | Play Testing Testing Record
Date | Test Case/Scenario | Name of Tester | Engagement - Gameplay | Engagement - Story/Lore | Test Results | Suggested Actions | Team Endorsement
2020-05-16 | General Play Testing | Trent | Sword monster is to overpowered, unbalanced, enemies attacking first makes it difficult to win | Needs addition to artwork and story. | Thought the game was alright, but needed to have work done on the battle's balance to make the game more enjoyable, with artwork and story adding to that that enjoyability. | Look at options for balancing the game, health and damage adjustments, move sets to give each monster an edge against the other. Look at producing more artwork and models for the game
2020-05-16 | General Play Testing | Richard | Pause Menu would be nice to allow players to go back to the mainmenu, quit button on the main menu doesn't work | Needs addition to artwork and story. | Thought the game was alright, but thought that additions could be added to the game to be more functional, easier to access settings and such. | Look into creating pause menu functionality and fixing the quit button. Create more visual assets for the game.
2020-05-16 | General Play Testing | David | ran at 60 FPS the whole time, with no lag. "Quit" button on the Menu didn't work A Reference sheet, or a tutorial on the controls/goals of the game would be nice to have A Healing mechanic, within the Battle menu, could help with making combat less difficult. A way to improve your monster could also help with the difficulty, EXP gain and leveling The three available monsters don't really feel any different from each other, maybe give them unique abilities | Environment is very bland, he player object doesn't stand out too well - consider giving the player object a unique colour The Hud and UI are damn good! Combat looks and feels very static - maybe add Animations for attacking/hurting would make it look nicer. Sound clips could also help | Enjoyed the game, found that the quit button didn't work, thought that more instructions would be helpful, suggested adding healing mechanics to battles to reduce difficulty of battles, suggested progression through monster leveling and making the monsters more unique. Believed that the game's art and animations should be improved. | Fix quit button and other functionalities, include short little paragraph that has a run down of the controls and some of the battle mechanics, look Healing and Leveling mechanics for the future development of the game. Improve upon visual assets and create new visual assets.
Note on H3: Record the frame rate of the application, CPU usage, GPU usage, and RAM usage in this section. This information can be found by viewing the performance tab of the task manager.